## Product Backlog
Planned Sprint | Actual Sprint |  | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | Sprint 1 | Sprint 1 | Select a dataset containing at least two cryptocurrencies — either by scraping from the web or downloading a CSV file. | MUST HAVE |  | vamsi krishna | 3- Completed
2 | Sprint 1 | Sprint 1 | Insert the collected data into a suitable database for further processing. | SHOULD HAVE |  | vamsi krishna | 3- Completed
3 | Sprint 1 | Sprint 1 | Compute various performance metrics for the data and save the results within a data frame. | MUST HAVE |  | vamsi krishna | 3- Completed
4 | Sprint 1 | Sprint 1 | Implement parallel processing techniques for the above operations to enhance efficiency. | SHOULD HAVE |  | vamsi krishna | 3- Completed
5 | Sprint 2 | Sprint 2 | Assign portfolio weights according to predefined rules (as mentioned in the September 1st slide) and compute both portfolio return and risk. | MUST HAVE |  | vamsi krishna | 3- Completed
6 | Sprint 2 | Sprint 2 | Design two database tables — one for portfolios and another for portfolio assets — to store currencies, weights, returns, risks, and metric values. | SHOULD HAVE |  | vamsi krishna | 3- Completed
7 | Sprint 2 | Sprint 2 | Implement functionality to store and retrieve portfolio data from the database. | SHOULD HAVE |  | vamsi krishna | 3- Completed
8 | Sprint 2 | Sprint 2 | Extend parallel execution by running multiple rule-based tests simultaneously (using ThreadPool), such as equal-weight, risk-based, and performance-based strategies, and save outputs into the database. | MUST HAVE |  | vamsi krishna | 3- Completed
9 | Sprint 3 | Sprint 3 | Compare returns between portfolio-based strategies and single asset investments using sample data. | MUST HAVE |  | vamsi krishna | 3- Completed
10 | Sprint 3 | Sprint 3 | Visualize the data by plotting graphs, derive insights, and export the results as a CSV file. | SHOULD HAVE |  | vamsi krishna | 3- Completed
11 | Sprint 3 | Sprint 3 | Prepare a markdown (.md) document summarizing all milestone 2 activities and progress. | MUST HAVE |  | vamsi krishna | 3- Completed
12 | Sprint 3 | Sprint 3 | Develop six different rules to identify portfolio risk, as referenced in the September 13th presentation. | SHOULD HAVE |  | vamsi krishna | 3- Completed
13 | Sprint 3 | Sprint 3 | Save all rules into the database and configure an automated email alert if any rule validation fails. | MUST HAVE |  | vamsi krishna | 3- Completed
14 | Sprint 3 | Sprint 3 | Use linear regression techniques to predict both overall portfolio returns and individual asset returns. | MUST HAVE |  | vamsi krishna | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 27 | 11 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US1 | 1 | Choose the data file with at least 2 cryptocurrencies (either web scrape CSV file or download to use as CSV). | 2025-08-18 | 2025-08-18 | Vamsi Krishna | Build | Completed | 1 | bar: Day 1
US2 | 2 | Store the data in the database. | 2025-08-19 | 2025-08-19 | Vamsi Krishna | Coding | Completed | 1 | bar: Day 1
US3 | 3 | Calculate the metrics for the data and store in the data frame. | 2025-08-22 | 2025-08-22 | Vamsi Krishna | Coding | Completed | 2 | bar: Day 1 to Day 2
US3 | 4 | Apply parallel tasks concepts to the above steps. | 2025-08-23 | 2025-08-23 | Vamsi Krishna | Coding | Completed | 2 | Day 1: 2
US3 | 5 | Assign weights for the portfolio. Check if weights are assigned based on the rule (mentioned in 1 September slide). Calculate portfolio return and portfolio risk. | 2025-08-25 | 2025-08-25 | Vamsi Krishna | Coding | Completed | 1 | bar: Day 1
US3 | 06- | Create two tables for portfolio and portfolio_assets to store currencies, weights, returns, risk, metrics. Store and fetch the data. | 2025-08-27 | 2025-08-27 | Vamsi Krishna | Unit Test | Completed | 11 | bar: Day 1
SPRINT 2 BACKLOG
US4 | 7 | Parallel Execution – Extend logic: run multiple rule tests in parallel (ThreadPool). Example: run equal-weight, risk-based, performance-based at same time. Save outputs into DB. | 2025-09-02 | 2025-09-02 | Vamsi Krishna | Coding | Completed | 1
US5 | 8 | Compare portfolio return vs. single asset return with some sample data. Plot the graphs, draw insights, export to CSV. | 2025-09-03 | 1900-01-03 | Vamsi Krishna | Coding | Completed | 2 | bar: Day 1
US6 | 9 | Prepare a .md file which should contain the Milestone 2 work completed so far. | 2025-09-05 | 2025-09-05 | Vamsi Krishna | Coding | Completed | 1
US7 | 10 | Implement 6 rules to identify risk (as per 13 Sep slide). | 2025-09-06 | 2025-09-06 | Vamsi Krishna | Coding | Completed | 2
SPRINT 3 BACKLOG
US8 | 11 | Store them in the database. Send email alert if any rule fails. | 2025-09-25 | 2025-09-27 | Vamsi Krishna | Coding | Completed | 1 | Day 1: 2
US9 | 12 | Predict both portfolio and individual returns using linear regression model. | 2025-10-04 | 2025-10-06 | Vamsi Krishna | Coding | Completed | 2 | bar: Day 1 to Day 2
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-08-13 | 2025-08-29 | Vamsi Krishna | Begin using at least two assets in the portfolio. | - | Keep maintaining accuracy in metric alignment. | Discussed with mentor and applied the rule to include at least two assets.
2 | Sprint 1 | 2013-08-13 | 2025-08-29 | Vamsi Krishna | Reassess and refine the logic behind metric calculations. | - | Continue using the present methods for metric calculations. | Revised and synchronized metric calculations as per mentor’s feedback.
3 | Sprint 2 | 2025-09-01 | 2025-09-12 | Vamsi Krishna | Incorporate three assets when calculating portfolio return weights. | - | Maintain focus on optimizing the portfolio. | Followed the suggested implementation successfully.
4 | Sprint 2 | 2025-09-01 | 2025-09-12 | Vamsi Krishna | Introduce limits for weight capping rules. | Avoid using unclear or undefined rules from earlier iterations. | Keep applying existing weight calculation rules. | Consulted mentor and enforced a 50% cap on weights.
5 | Sprint 2 | 2025-09-01 | 2025-09-12 | Vamsi Krishna | Create one portfolio return vs. asset plot. | Eliminate plotting multiple return graphs unnecessarily. | Continue generating portfolio return plots. | Executed the plotting rule as per mentor’s advice.
6 | Sprint 3 | 2025-09-15 | 2025-09-26 | Vamsi Krishna | Establish a linear relationship for the regression model. | Stop ignoring linear dependencies in regression. | Maintain efforts in performance improvement. | Verified which variables show linear dependency in returns.
7 | Sprint 3 | 2025-09-15 | 2025-09-26 | Vamsi Krishna | Enhance features that better match asset-level prediction accuracy. | Remove features that don’t add value to prediction accuracy. | Keep predicting portfolio returns and USDC values effectively. | Used KBest method for feature selection and applied standard scaling.
8 | Sprint 3 | 2025-09-30 | 2025-10-04 | Vamsi Krishna | Implement an investment diversification strategy. | Discontinue the equal weight approach. | Continue following any valid investment rules. | Referred to presentation slides from the 30th step to interpret the rule correctly.
9 | Sprint 3 | 2025-09-30 | 2025-10-04 | Vamsi Krishna | Conduct stress testing for portfolio performance. | - | Keep simulating portfolio performance under various market scenarios. | Tested portfolio weight rules with sample data under different market situations.